## Start Here
Commercial Greenhouse Project Feasibility Gate Workbook
Decide what must be proven before land, equipment or construction commitments. Unknown evidence is shown as a decision risk, not silently treated as a positive answer.
Project name | Site / country | Buyer lead | Revision date
Decision gates | Unresolved | Stop signals | Readiness
32 | 32 | 0 | 0%
Buyer workflow
1. Define the project case and commercial objective before evaluating technology.
2. Answer every gate with evidence; use Unknown where evidence is missing.
3. Do not sign a binding equipment order while any critical gate shows STOP.
4. Assign owners and dates for unresolved evidence, then repeat the review.
5. Record the decision conditions in the Decision Memo.
Important: Buyer-use screening and evidence-control tool. It does not replace crop-specific agronomy, a qualified local engineer, laboratory interpretation, legal advice, authority approval, the signed contract, or project-specific design calculations.

## Project Case
Project Case and Decision Boundary
State what the project is expected to achieve and what is outside this decision.
Project input | Buyer entry | Unit / format | Why it matters | Evidence / source | Confirmed by
Project name |  | Text | Controls all records and revisions.
Country, site and coordinates |  | Text / coordinates | Connects climate, code, logistics and authority checks.
Target crop(s) and cultivar strategy |  | Text | Defines production and environmental assumptions.
Target customer / sales channel |  | Text | Defines grade, packaging, timing and price evidence.
Target production and harvest windows |  | Dates / seasons | Tests whether the greenhouse solves a market-timing problem.
Planned production area and expansion phase |  | m² / phases | Separates first-stage needs from future assumptions.
Production system |  | Soil / substrate / hydroponic | Determines root-zone, drainage, hygiene and irrigation requirements.
Owner capex boundary |  | Currency / amount | Must include local works, tax, freight and contingency.
Operating-cost boundary |  | Currency / period | Defines included labor, energy, water, consumables and maintenance.
Target crop-entry date |  | yyyy-mm-dd | Must be checked against approvals, design and installation dependencies.
Decision authority |  | Name / role | Identifies who can approve, hold or stop the project.
Decision being made now |  | Text | Prevents a concept review from being mistaken for final investment approval.
Explicit exclusions |  | Text | Records what this gate review does not prove.
Important: Buyer-use screening and evidence-control tool. It does not replace crop-specific agronomy, a qualified local engineer, laboratory interpretation, legal advice, authority approval, the signed contract, or project-specific design calculations.

## Gate Review
Evidence-Based Feasibility Gate Review
Do not replace Unknown with Yes to improve the score. A buyer benefits more from an early, visible gap than a late project surprise.
ID | Area | Buyer decision question | Evidence to obtain | Critical? | Buyer answer | Confidence | Risk if unresolved | Next action | Owner | Due date | Gate status
F-01 | Market | Is the target customer and sales channel identified? | Written channel plan, buyer interviews or off-take evidence | Yes | Unknown | Low | A technically successful crop may still have no profitable route to market. |  |  |  | UNRESOLVED
F-02 | Market | Are product grades, pack formats and rejection rules known? | Buyer specification and sample quality standard | Yes | Unknown | Low | Yield assumptions are meaningless if saleable grade is undefined. |  |  |  | UNRESOLVED
F-03 | Market | Is the planned harvest window commercially valuable? | Seasonal price history and competitor supply calendar | Yes | Unknown | Low | A greenhouse cannot recover a premium that does not exist. |  |  |  | UNRESOLVED
F-04 | Market | Are cold-chain, packing and dispatch responsibilities defined? | Process map, capacity and logistics quotations | No | Unknown | Low | Post-harvest losses can erase production gains. |  |  |  | UNRESOLVED
F-05 | Crop | Has a crop and cultivar strategy been agreed for the local market and climate? | Agronomist brief, cultivar evidence and trial history | Yes | Unknown | Low | The structure and systems depend on crop biology and production goals. |  |  |  | UNRESOLVED
F-06 | Crop | Is the production system defined: soil, substrate, hydroponic, benches or containers? | Crop-system concept and root-zone requirements | Yes | Unknown | Low | Drainage, irrigation, floor and hygiene requirements change with the system. |  |  |  | UNRESOLVED
F-07 | Crop | Are realistic planting, establishment and ramp-up periods included? | Crop calendar and labor plan | No | Unknown | Low | Full-output assumptions in year one can distort cash planning. |  |  |  | UNRESOLVED
F-08 | Crop | Are pollination, pruning, trellising and crop-work methods known? | Operating method and labor-minute estimate | No | Unknown | Low | Structure height and internal layout may become operational constraints. |  |  |  | UNRESOLVED
F-09 | Climate | Are hourly or percentile weather data available, not only monthly averages? | Accepted weather file, station record and source note | Yes | Unknown | Low | Monthly averages hide peak cooling, heating and condensation conditions. |  |  |  | UNRESOLVED
F-10 | Climate | Are extreme wind, snow, hail, flood and seismic conditions identified? | Local code basis and qualified design input | Yes | Unknown | Low | Structural risk cannot be priced responsibly without a site basis. |  |  |  | UNRESOLVED
F-11 | Climate | Are crop-stage indoor targets and allowable excursions defined? | Grower-approved environmental brief | Yes | Unknown | Low | Equipment cannot be selected from an undefined performance target. |  |  |  | UNRESOLVED
F-12 | Climate | Has condensation and high-humidity risk been considered? | Psychrometric or operational review and control concept | No | Unknown | Low | A temperature-only design may create disease and quality problems. |  |  |  | UNRESOLVED
F-13 | Site | Does the owner control the land for the required project life? | Title, lease and encumbrance review | Yes | Unknown | Low | Do not commit equipment before land rights are secure. |  |  |  | UNRESOLVED
F-14 | Site | Are zoning, permits, setbacks and environmental approvals feasible? | Written authority checks and permit register | Yes | Unknown | Low | A valid structure proposal can still be unbuildable on the selected site. |  |  |  | UNRESOLVED
F-15 | Site | Are topography, drainage, flood pathways and finished levels understood? | Survey, drainage concept and flood evidence | Yes | Unknown | Low | Poor levels affect foundations, water entry, roads and crop hygiene. |  |  |  | UNRESOLVED
F-16 | Site | Can trucks, cranes and emergency services access the site year-round? | Access drawing, turning review and seasonal observation | No | Unknown | Low | Last-mile constraints create installation delays and operating risk. |  |  |  | UNRESOLVED
F-17 | Water | Has source water been laboratory tested for crop and equipment suitability? | Dated agricultural irrigation-water report | Yes | Unknown | Low | pH alone does not describe alkalinity, salinity, ions or clogging risk. |  |  |  | UNRESOLVED
F-18 | Water | Is peak source flow confirmed by a witnessed test? | Flow/pressure test with date, method and seasonal context | Yes | Unknown | Low | Nameplate well capacity is not the same as reliable peak supply. |  |  |  | UNRESOLVED
F-19 | Water | Are storage, treatment, rainwater, drainage and discharge routes defined? | Water balance and concept drawing | No | Unknown | Low | Irrigation, cooling and cleaning can compete for limited water. |  |  |  | UNRESOLVED
F-20 | Energy | Are available voltage, phases, frequency, capacity and reliability confirmed? | Utility letter, load study and outage history | Yes | Unknown | Low | Incorrect power assumptions can force redesign or generator dependence. |  |  |  | UNRESOLVED
F-21 | Energy | Are fuel availability and delivered energy costs known where heating is considered? | Supplier evidence and seasonal price cases | No | Unknown | Low | A low-capex heating choice may have an unworkable operating cost. |  |  |  | UNRESOLVED
F-22 | Energy | Is backup power defined by protected loads and required autonomy? | Critical-load list and resilience decision | No | Unknown | Low | A generator sized without load priorities can still fail the crop. |  |  |  | UNRESOLVED
F-23 | Labor | Are skilled crop, maintenance and control-system operators available? | Organization chart, hiring evidence and training plan | Yes | Unknown | Low | Automation does not remove the need for competent decisions and maintenance. |  |  |  | UNRESOLVED
F-24 | Labor | Are peak harvest and crop-work labor requirements realistic? | Peak-week labor model and local availability check | No | Unknown | Low | Labor bottlenecks can reduce quality even when climate control performs. |  |  |  | UNRESOLVED
F-25 | Operations | Who owns agronomy, facilities, maintenance and data review after handover? | Named roles, escalation map and budget | Yes | Unknown | Low | Unowned interfaces become chronic failures. |  |  |  | UNRESOLVED
F-26 | Operations | Is spare-parts and local service support defined? | Critical spares list, response times and support boundary | No | Unknown | Low | Small unavailable parts can stop high-value production. |  |  |  | UNRESOLVED
F-27 | Commercial | Is the budget based on a defined scope and local cost boundary? | Cost plan with inclusions, exclusions, tax, freight and contingency | Yes | Unknown | Low | A structure-only price is not a project budget. |  |  |  | UNRESOLVED
F-28 | Commercial | Are working capital and crop ramp-up funded separately from construction? | Cash plan covering inputs, labor, utilities and sales delay | Yes | Unknown | Low | A finished greenhouse can fail before stable revenue begins. |  |  |  | UNRESOLVED
F-29 | Commercial | Have downside cases been tested for price, saleable yield, delay and energy? | Sensitivity table with owner-approved cases | Yes | Unknown | Low | A single optimistic forecast hides decision risk. |  |  |  | UNRESOLVED
F-30 | Delivery | Is the target crop-entry date compatible with permits, design, manufacture, shipping and commissioning? | Integrated schedule with dependencies and float | No | Unknown | Low | A promised shipment date is not a crop-entry date. |  |  |  | UNRESOLVED
F-31 | Delivery | Are owner works and supplier interfaces scheduled and assigned? | Responsibility matrix and interface milestones | Yes | Unknown | Low | Foundations, utilities and controls often fail at contract boundaries. |  |  |  | UNRESOLVED
F-32 | Governance | Is there a written stage-gate decision and named approval authority? | Signed decision memo with conditions and evidence gaps | Yes | Unknown | Low | Unrecorded assumptions become commitments without ownership. |  |  |  | UNRESOLVED
Important: Buyer-use screening and evidence-control tool. It does not replace crop-specific agronomy, a qualified local engineer, laboratory interpretation, legal advice, authority approval, the signed contract, or project-specific design calculations.

## Decision Memo
Buyer Decision Memo
Capture the decision and its conditions. A conditional approval should list evidence, owner and deadline rather than rely on meeting notes.
Decision item | Buyer entry | Evidence / reference | Owner | Due date | Closeout status
Decision date |  |  |  |  | Open
Decision: proceed / hold / stop |  |  |  |  | Open
Approved project boundary |  |  |  |  | Open
Critical evidence still missing |  |  |  |  | Open
Conditions before RFQ |  |  |  |  | Open
Conditions before contract |  |  |  |  | Open
Conditions before construction |  |  |  |  | Open
Downside case accepted by |  |  |  |  | Open
Next formal review date |  |  |  |  | Open
Decision authority sign-off |  |  |  |  | Open
Important: Buyer-use screening and evidence-control tool. It does not replace crop-specific agronomy, a qualified local engineer, laboratory interpretation, legal advice, authority approval, the signed contract, or project-specific design calculations.

## Sources
Sources and Project-Specific Evidence
Use these as orientation only. Record the controlling local code, crop adviser, laboratory, weather source, contract and approved project documents for the actual project.
ID | Source owner | Document / resource | How to use it | URL or project reference
S-01 | FAO | Good Agricultural Practices for greenhouse vegetable crops | Protected-cropping context; adapt to crop and region. | https://www.fao.org/4/i3284e/i3284e.pdf
S-02 | UMass Extension | Greenhouse Best Management Practices Manual | Water, irrigation, crop and operating practices. | https://www.umass.edu/agriculture-food-environment/book/export/html/9854
S-03 | UMass Extension | Water Analysis | Test source water before construction; interpret it for the selected crop and system. | https://www.umass.edu/agriculture-food-environment/greenhouse-floriculture/greenhouse-best-management-practices-bmp-manual/water-analysis
S-04 | NASA POWER | Global meteorology and solar-energy data | Screening data only; confirm design conditions with accepted local sources. | https://power.larc.nasa.gov/data-access-viewer/
S-05 | ASHRAE | Climatic design information | One possible source for outdoor design conditions where applicable. | https://www.ashrae.org/technical-resources/bookstore/ashrae-climatic-design-conditions-2009-2017
S-06 | Local authority | Building, fire, electrical, water, environmental and planning requirements | The authority having jurisdiction and local professionals control project compliance. | Owner to enter local URLs and document references
S-07 | Project contract | Owner requirements, responsibility matrix and acceptance basis | The signed project documents control scope, interfaces and acceptance. | Owner-controlled document
Important: Buyer-use screening and evidence-control tool. It does not replace crop-specific agronomy, a qualified local engineer, laboratory interpretation, legal advice, authority approval, the signed contract, or project-specific design calculations.